## Sheet1
Program | Milestone ID | Milestone | Workstream | Business Area | Owner | Status | RAG | % Complete | Baseline Start | Actual Start | Baseline Finish | Actual Finish | Last Reviewed | Effort (hrs)
S4 Modernization | MS-001 | Decommission Data & Cutover API contract | Regional Rollout | Manufacturing | Nora Lindqvist | In Progress | Green | 44 | 2026-04-29 | 2026-05-06 | 2026-07-30 |  | 2026-08-30 | 12
S4 Modernization | MS-002 | Validate Regional Rollout data model | OCM | Commercial | Priya Nandakumar | Not Started | Amber | 0 | 2026-04-13 |  | 2026-07-04 |  | 2026-05-23 | 8
S4 Modernization | MS-003 | Validate Data & Cutover test script | Data & Cutover | Supply Chain | Marta Kowalski | In Progress | Green | 11 | 2026-03-20 | 2026-03-27 | 2026-11-30 |  | 2026-08-15 | 39
S4 Modernization | MS-004 | Build OCM audit trail | Data & Cutover | Finance | Marta Kowalski | Complete | Green | 100 | 2025-12-31 | 2026-01-03 | 2026-05-07 | 2026-06-03 | 2026-06-03 | 5
S4 Modernization | MS-005 | Integrate Regional Rollout API contract | OCM | Finance | Sean Gallagher | In Progress | Green | 60 | 2026-01-15 | 2026-01-16 | 2026-02-18 |  | 2026-08-30 | 39
S4 Modernization | MS-006 | Document Data & Cutover master record | Global Template | Finance | Rajesh Iyer | In Progress | Green | 15 | 2026-04-20 | 2026-04-23 | 2026-07-20 |  | 2026-08-24 | 50
S4 Modernization | MS-007 | Refactor Global Template data model | Regional Rollout | Finance | Amara Okafor | In Progress | Green | 73 | 2025-10-18 | 2025-10-25 | 2026-01-19 |  | 2026-08-10 | 36
S4 Modernization | MS-008 | Configure Regional Rollout approval workflow | Data & Cutover | Supply Chain | Hiroshi Tanaka | Blocked | Red | 12 | 2026-07-15 | 2026-07-20 | 2026-12-07 |  | 2026-07-15 | 20
S4 Modernization | MS-009 | Configure OCM dashboard | Global Template | Finance | Daniel Osei | Not Started | Amber | 0 | 2026-06-19 |  | 2026-10-25 |  | 2026-06-19 | 40
S4 Modernization | MS-010 | Document Data & Cutover API contract | Global Template | Manufacturing | Marta Kowalski | In Progress | Green | 44 | 2025-06-09 | 2025-06-16 | 2025-09-12 |  | 2026-08-31 | 28
S4 Modernization | MS-011 | Design Global Template reconciliation | Global Template | Finance | Marta Kowalski | Blocked | Red | 47 | 2025-08-24 | 2025-08-27 | 2026-01-19 |  | 2026-07-01 | 12
S4 Modernization | MS-012 | Configure Data & Cutover master record | OCM | Manufacturing | Priya Nandakumar | In Progress | Green | 81 | 2025-12-26 | 2026-01-08 | 2026-04-18 |  | 2026-08-31 | 127
S4 Modernization | MS-013 | Deploy OCM training module | Data & Cutover | Supply Chain | Marta Kowalski | Not Started | Amber | 0 | 2026-04-09 |  | 2026-06-19 |  | 2026-06-13 | 17
S4 Modernization | MS-014 | Decommission Global Template test script | Regional Rollout | Manufacturing | Lucia Ferrari | Complete | Green | 100 | 2025-10-14 | 2025-10-19 | 2026-01-20 | 2026-01-03 | 2026-01-03 | 48
S4 Modernization | MS-015 | Deploy Global Template audit trail | Data & Cutover | Manufacturing | Amara Okafor | Complete | Green | 100 | 2025-11-14 | 2025-11-25 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 3
S4 Modernization | MS-016 | Configure Regional Rollout reporting extract | Data & Cutover | Commercial | Sean Gallagher | Blocked | Red | 81 | 2025-09-29 | 2025-10-04 | 2025-12-23 |  | 2026-05-21 | 76
S4 Modernization | MS-017 | Decommission Data & Cutover reconciliation | OCM | Supply Chain | Daniel Osei | Not Started | Amber | 0 | 2026-01-04 |  | 2026-01-26 |  | 2026-06-21 | 90
S4 Modernization | MS-018 | Test Regional Rollout user role | OCM | Supply Chain | Marta Kowalski | Not Started | Amber | 0 | 2025-12-15 |  | 2026-02-18 |  | 2026-08-16 | 25
S4 Modernization | MS-019 | Onboard OCM user role | OCM | Manufacturing | Priya Nandakumar | Not Started | Amber | 0 | 2025-09-11 |  | 2025-12-12 |  | 2026-03-03 | 40
S4 Modernization | MS-020 | Configure OCM approval workflow | Global Template | Manufacturing | Daniel Osei | Not Started | Amber | 0 | 2026-01-14 |  | 2026-03-23 |  | 2026-07-25 | 40
S4 Modernization | MS-021 | Deploy Data & Cutover interface | OCM | Supply Chain | Marta Kowalski | In Progress | Green | 48 | 2025-10-14 | 2025-10-20 | 2025-12-15 |  | 2026-08-30 | 13
S4 Modernization | MS-022 | Build Regional Rollout batch job | Regional Rollout | Manufacturing | Priya Nandakumar | Complete | Green | 100 | 2025-10-18 | 2025-10-26 | 2026-02-04 | 2026-02-24 | 2026-02-24 | 39
S4 Modernization | MS-023 | Deploy Global Template conversion rule | Regional Rollout | Supply Chain | Priya Nandakumar | Complete | Green | 100 | 2025-11-13 | 2025-11-16 | 2026-01-08 | 2026-01-01 | 2026-01-01 | 12
S4 Modernization | MS-024 | Configure OCM approval workflow | Data & Cutover | Supply Chain | Amara Okafor | Complete | Green | 100 | 2026-03-23 | 2026-03-26 | 2026-05-01 | 2026-04-27 | 2026-04-27 | 14
S4 Modernization | MS-025 | Reconcile OCM audit trail | Data & Cutover | Supply Chain | Marta Kowalski | In Progress | Green | 62 | 2025-12-22 | 2025-12-27 | 2026-04-01 |  | 2026-08-24 | 66
S4 Modernization | MS-026 | Design Regional Rollout approval workflow | Regional Rollout | Commercial | Daniel Osei | Blocked | Red | 48 | 2026-01-03 | 2026-01-14 | 2026-07-09 |  | 2026-05-22 | 58
S4 Modernization | MS-027 | Refactor Data & Cutover reporting extract | OCM | Manufacturing | Priya Nandakumar | In Progress | Green | 33 | 2025-08-16 | 2025-08-18 | 2026-06-07 |  | 2026-08-19 | 13
S4 Modernization | MS-028 | Build OCM dashboard | Global Template | Finance | Marta Kowalski | Blocked | Red | 41 | 2025-11-16 | 2025-11-22 | 2026-03-24 |  | 2026-07-14 | 12
S4 Modernization | MS-029 | Refactor Data & Cutover reconciliation | Global Template | Commercial | Marta Kowalski | Blocked | Red | 47 | 2025-12-25 | 2026-01-03 | 2026-02-05 |  | 2026-06-26 | 13
S4 Modernization | MS-030 | Document Global Template reporting extract | Global Template | Manufacturing | Marta Kowalski | Not Started | Amber | 0 | 2025-10-05 |  | 2025-12-09 |  | 2026-07-21 | 46
S4 Modernization | MS-031 | Decommission Data & Cutover training module | OCM | Finance | Hiroshi Tanaka | Not Started | Amber | 0 | 2026-05-27 |  | 2026-09-16 |  | 2026-05-27 | 10
S4 Modernization | MS-032 | Refactor OCM approval workflow | Regional Rollout | Manufacturing | Priya Nandakumar | In Progress | Green | 69 | 2026-02-04 | 2026-02-13 | 2026-05-19 |  | 2026-08-21 | 33
S4 Modernization | MS-033 | Integrate OCM approval workflow | Regional Rollout | Manufacturing | Rajesh Iyer | In Progress | Green | 12 | 2025-11-25 | 2025-12-01 | 2026-04-08 |  | 2026-08-26 | 47
S4 Modernization | MS-034 | Build Regional Rollout cutover task | Data & Cutover | Commercial | Priya Nandakumar | Not Started | Amber | 0 | 2026-01-11 |  | 2026-03-01 |  | 2026-03-13 | 22
S4 Modernization | MS-035 | Deploy Data & Cutover user role | Regional Rollout | Supply Chain | Marta Kowalski | Not Started | Amber | 0 | 2026-04-29 |  | 2026-08-22 |  | 2026-04-29 | 60
S4 Modernization | MS-036 | Document Regional Rollout interface | Data & Cutover | Manufacturing | Priya Nandakumar | In Progress | Green | 84 | 2026-05-10 | 2026-05-11 | 2026-10-12 |  | 2026-09-02 | 18
S4 Modernization | MS-037 | Design Data & Cutover audit trail | Global Template | Supply Chain | Marta Kowalski | In Progress | Green | 45 | 2026-04-22 | 2026-04-22 | 2026-10-31 |  | 2026-08-18 | 20
S4 Modernization | MS-038 | Deploy Global Template user role | Global Template | Supply Chain | Daniel Osei | Not Started | Amber | 0 | 2025-08-07 |  | 2025-10-11 |  | 2026-06-09 | 10
S4 Modernization | MS-039 | Configure Regional Rollout reporting extract | OCM | Manufacturing | Lucia Ferrari | Not Started | Amber | 0 | 2025-08-28 |  | 2025-11-18 |  | 2026-06-26 | 60
S4 Modernization | MS-040 | Migrate Regional Rollout user role | Regional Rollout | Commercial | Daniel Osei | Complete | Green | 100 | 2026-05-02 | 2026-05-08 | 2026-05-16 | 2026-05-20 | 2026-05-20 | 12
S4 Modernization | MS-041 | Design Regional Rollout dashboard | Global Template | Commercial | Hiroshi Tanaka | In Progress | Green | 62 | 2026-02-03 | 2026-02-14 | 2026-04-20 |  | 2026-08-10 | 33
S4 Modernization | MS-042 | Integrate Regional Rollout reporting extract | Regional Rollout | Commercial | Priya Nandakumar | Not Started | Amber | 0 | 2026-04-07 |  | 2026-06-20 |  | 2026-04-07 | 23
S4 Modernization | MS-043 | Migrate Global Template test script | Regional Rollout | Manufacturing | Priya Nandakumar | Complete | Green | 100 | 2025-10-30 | 2025-10-30 | 2025-12-15 | 2025-12-19 | 2025-12-19 | 9
S4 Modernization | MS-044 | Build Data & Cutover audit trail | Regional Rollout | Manufacturing | Daniel Osei | Not Started | Amber | 0 | 2025-10-17 |  | 2026-01-25 |  | 2026-04-13 | 14
S4 Modernization | MS-045 | Document Regional Rollout training module | Regional Rollout | Supply Chain | Marta Kowalski | Complete | Green | 100 | 2025-06-02 | 2025-06-14 | 2025-09-30 | 2025-06-20 | 2025-06-20 | 83
S4 Modernization | MS-046 | Migrate OCM data model | Data & Cutover | Commercial | Marta Kowalski | Blocked | Red | 13 | 2025-08-12 | 2025-08-21 | 2025-09-07 |  | 2026-07-18 | 29
S4 Modernization | MS-047 | Build Global Template reconciliation | Global Template | Supply Chain | Nora Lindqvist | In Progress | Green | 48 | 2026-06-30 | 2026-06-30 | 2026-10-20 |  | 2026-08-10 | 10
S4 Modernization | MS-048 | Document Data & Cutover API contract | Regional Rollout | Supply Chain | Amara Okafor | Complete | Green | 100 | 2026-01-02 | 2026-01-06 | 2026-03-03 | 2026-02-25 | 2026-02-25 | 32
S4 Modernization | MS-049 | Design Global Template cutover task | Regional Rollout | Commercial | Nora Lindqvist | Not Started | Amber | 0 | 2026-03-28 |  | 2026-08-03 |  | 2026-07-22 | 21
S4 Modernization | MS-050 | Decommission Data & Cutover reporting extract | Data & Cutover | Manufacturing | Daniel Osei | In Progress | Green | 74 | 2026-07-01 | 2026-07-04 | 2026-08-14 |  | 2026-08-20 | 537
S4 Modernization | MS-051 | Document Regional Rollout training module | OCM | Supply Chain | Sean Gallagher | Not Started | Amber | 0 | 2026-05-31 |  | 2026-08-28 |  | 2026-08-05 | 31
S4 Modernization | MS-052 | Decommission Regional Rollout approval workflow | OCM | Commercial | Hiroshi Tanaka | In Progress | Green | 31 | 2025-08-05 | 2025-08-18 | 2025-10-25 |  | 2026-08-19 | 17
S4 Modernization | MS-053 | Reconcile Data & Cutover audit trail | Regional Rollout | Commercial | Hiroshi Tanaka | Not Started | Amber | 0 | 2025-11-19 |  | 2026-04-01 |  | 2026-04-22 | 86
S4 Modernization | MS-054 | Decommission OCM reconciliation | Data & Cutover | Supply Chain | Nora Lindqvist | Not Started | Amber | 0 | 2026-01-11 |  | 2026-03-31 |  | 2026-08-10 | 5
S4 Modernization | MS-055 | Test Regional Rollout audit trail | Global Template | Manufacturing | Amara Okafor | Blocked | Red | 82 | 2026-04-29 | 2026-05-06 | 2026-08-07 |  | 2026-06-04 | 26
S4 Modernization | MS-056 | Integrate OCM cutover task | Data & Cutover | Supply Chain | Rajesh Iyer | In Progress | Green | 10 | 2025-12-17 | 2025-12-21 | 2026-01-20 |  | 2026-08-17 | 144
S4 Modernization | MS-057 | Onboard Global Template API contract | Global Template | Manufacturing | Amara Okafor | Not Started | Amber | 0 | 2025-09-04 |  | 2025-10-18 |  | 2026-06-25 | 22
S4 Modernization | MS-058 | Build Regional Rollout conversion rule | Global Template | Commercial | Priya Nandakumar | Blocked | Red | 36 | 2025-11-08 | 2025-11-11 | 2026-01-22 |  | 2026-08-10 | 5
S4 Modernization | MS-059 | Automate Regional Rollout reporting extract | Data & Cutover | Manufacturing | Amara Okafor | Not Started | Amber | 0 | 2025-06-09 |  | 2025-09-25 |  | 2026-05-19 | 17
S4 Modernization | MS-060 | Validate OCM training module | Global Template | Commercial | Marta Kowalski | In Progress | Green | 56 | 2026-01-23 | 2026-01-30 | 2026-04-06 |  | 2026-08-23 | 89
S4 Modernization | MS-061 | Design Global Template audit trail | Regional Rollout | Manufacturing | Rajesh Iyer | In Progress | Green | 68 | 2026-03-06 | 2026-03-06 | 2026-09-08 |  | 2026-08-09 | 34
S4 Modernization | MS-062 | Migrate Regional Rollout dashboard | Global Template | Commercial | Sean Gallagher | Complete | Green | 100 | 2026-03-04 | 2026-03-07 | 2026-05-27 | 2026-05-23 | 2026-05-23 | 11
S4 Modernization | MS-063 | Migrate Regional Rollout API contract | Data & Cutover | Supply Chain | Priya Nandakumar | Not Started | Amber | 0 | 2026-04-03 |  | 2026-06-04 |  | 2026-04-03 | 13
S4 Modernization | MS-064 | Design OCM dashboard | OCM | Supply Chain | Priya Nandakumar | Deferred | Grey | 0 | 2026-04-18 |  | 2026-07-21 | 2026-07-07 | 2026-07-07 | 15
S4 WS 4A | MS-001 | Design Validation reconciliation | Integration Build | Quality | Priya Nandakumar | In Progress | Green | 42 | 2026-05-27 | 2026-06-04 | 2026-09-28 |  | 2026-08-13 | 13
S4 WS 4A | MS-002 | Migrate Process Design test script | Validation | Manufacturing | Priya Nandakumar | Not Started | Amber | 0 | 2026-07-10 |  | 2027-02-06 |  | 2026-07-10 | 33
S4 WS 4A | MS-003 | Reconcile Validation cutover task | Validation | Quality | Daniel Osei | In Progress | Green | 38 | 2026-05-17 | 2026-05-18 | 2026-12-18 |  | 2026-08-19 | 119
S4 WS 4A | MS-004 | Automate Integration Build data model | Process Design | Quality | Priya Nandakumar | Deferred | Grey | 0 | 2026-03-11 |  | 2026-08-16 | 2026-08-06 | 2026-08-06 | 103
S4 WS 4A | MS-005 | Build Validation test script | Validation | Manufacturing | Priya Nandakumar | Not Started | Amber | 0 | 2026-02-23 |  | 2027-01-29 |  | 2026-07-19 | 33
S4 WS 4A | MS-006 | Configure Validation batch job | Validation | Manufacturing | Marta Kowalski | Complete | Green | 100 | 2026-05-01 | 2026-05-04 | 2026-08-18 | 2026-07-27 | 2026-07-27 | 36
S4 WS 4A | MS-007 | Test Process Design user role | Validation | Quality | Priya Nandakumar | Complete | Green | 100 | 2026-01-05 | 2026-01-09 | 2027-02-14 | 2026-02-26 | 2026-02-26 | 49
S4 WS 4A | MS-008 | Refactor Process Design data model | Process Design | Quality | Priya Nandakumar | Complete | Green | 100 | 2026-01-05 | 2026-01-14 | 2026-05-10 | 2026-01-30 | 2026-01-30 | 8
S4 WS 4A | MS-009 | Decommission Integration Build API contract | Validation | Quality | Priya Nandakumar | Not Started | Amber | 0 | 2026-03-12 |  | 2028-04-13 |  | 2026-07-16 | 43
S4 WS 4A | MS-010 | Onboard Process Design API contract | Process Design | Quality | Priya Nandakumar | Not Started | Amber | 0 | 2026-08-28 |  | 2026-10-18 |  | 2026-08-30 | 12
S4 WS 4A | MS-011 | Configure Process Design dashboard | Process Design | Quality | Daniel Osei | Blocked | Red | 76 | 2026-03-30 | 2026-04-05 | 2026-06-12 |  | 2026-08-14 | 32
S4 WS 4A | MS-012 | Design Validation conversion rule | Validation | Quality | Priya Nandakumar | Blocked | Red | 68 | 2026-03-19 | 2026-03-31 | 2026-08-15 |  | 2026-07-16 | 20
S4 WS 4A | MS-013 | Deploy Validation training module | Process Design | Quality | Priya Nandakumar | Not Started | Amber | 0 | 2026-03-21 |  | 2026-09-15 |  | 2026-06-24 | 38
S4 WS 4A | MS-014 | Test Integration Build test script | Validation | Manufacturing | Hiroshi Tanaka | Not Started | Amber | 0 | 2026-02-23 |  | 2027-05-16 |  | 2026-07-13 | 27
S4 WS 4A | MS-015 | Reconcile Process Design conversion rule | Integration Build | Quality | Hiroshi Tanaka | Not Started | Amber | 0 | 2026-05-07 |  | 2026-07-01 |  | 2026-07-31 | 2
S4 WS 4A | MS-016 | Deploy Process Design training module | Process Design | Quality | Priya Nandakumar | Not Started | Amber | 0 | 2026-05-03 |  | 2026-11-16 |  | 2026-05-03 | 28
S4 WS 4A | MS-017 | Test Validation API contract | Process Design | Manufacturing | Priya Nandakumar | Not Started | Amber | 0 | 2026-05-04 |  | 2027-01-12 |  | 2026-05-04 | 43
S4 WS 4A | MS-018 | Validate Process Design API contract | Validation | Quality | Daniel Osei | Deferred | Grey | 0 | 2026-01-05 |  | 2026-06-29 | 2026-05-20 | 2026-05-20 | 36
S4 WS 4A | MS-019 | Build Process Design user role | Validation | Quality | Marta Kowalski | Blocked | Red | 75 | 2026-05-04 | 2026-05-08 | 2026-06-23 |  | 2026-06-11 | 22
S4 WS 4A | MS-020 | Reconcile Integration Build conversion rule | Integration Build | Manufacturing | Marta Kowalski | Complete | Green | 100 | 2026-01-05 | 2026-01-13 | 2026-09-22 | 2026-08-30 | 2026-08-30 | 105
S4 WS 4A | MS-021 | Automate Integration Build data model | Validation | Manufacturing | Priya Nandakumar | In Progress | Green | 29 | 2026-03-29 | 2026-04-08 | 2026-11-19 |  | 2026-08-15 | 32
S4 WS 4A | MS-022 | Configure Integration Build batch job | Process Design | Manufacturing | Priya Nandakumar | Not Started | Amber | 0 | 2026-02-01 |  | 2026-06-19 |  | 2026-08-26 | 36
S4 WS 4A | MS-023 | Refactor Integration Build audit trail | Integration Build | Manufacturing | Daniel Osei | Blocked | Red | 73 | 2026-03-08 | 2026-03-21 | 2026-08-05 |  | 2026-06-29 | 61
S4 WS 4A | MS-024 | Integrate Validation cutover task | Process Design | Manufacturing | Hiroshi Tanaka | Not Started | Amber | 0 | 2026-07-23 |  | 2026-11-19 |  | 2026-07-23 | 33
S4 WS 4A | MS-025 | Document Integration Build data model | Integration Build | Manufacturing | Hiroshi Tanaka | Not Started | Amber | 0 | 2026-05-11 |  | 2026-09-04 |  | 2026-05-11 | 11
S4 WS 4A | MS-026 | Automate Validation dashboard | Process Design | Manufacturing | Priya Nandakumar | Not Started | Amber | 0 | 2026-02-27 |  | 2026-08-19 |  | 2026-02-27 | 3
S4 WS 4A | MS-027 | Automate Integration Build approval workflow | Integration Build | Manufacturing | Daniel Osei | Not Started | Amber | 0 | 2026-07-28 |  | 2026-12-18 |  | 2026-07-28 | 16
S4 WS 4A | MS-028 | Configure Integration Build cutover task | Integration Build | Manufacturing | Priya Nandakumar | In Progress | Green | 42 | 2026-02-02 | 2026-02-05 | 2026-03-28 |  | 2026-08-21 | 48